## Instructions
Purpose
Simple Product Backlog spreadsheet to display basic information such as the release burn-up, scope change over time, likely release date, ability to make commitments, and how much interuptions we are seeing
Lookups
Fill in the values you'd like to select against for the following categories:
Usage
Enter data into the "Product Backlog" tab.
When you have decided on a plan for a "Release Event" set the Scope to "Baseline". Future scope added to this "Release Event" should be Scoped as "Added".
At the end of the Sprint we need to update the "Velocity History" tab with the information about the Sprint. Use the "Raw Calculations" tab to get some of this data
Charts will update automatically after you enter the Sprint data.

## Lookups
Relative Size | Scope Change | Investment Category | Investment Category Description | Release Event | Epic | Status | Schedule | Project | Committed | Normal Variation
1 | Baselined | Project / New Feature | General incremental IT Services investments required to address market/customer demand. | Bootstrap | Epic 1 | To Do | Sprint 1 | Centennial | Committed | 16%
2 | Added | R&D | Truly new work. Investment in IT Services that is totally new to the work or to our offering to the industry / market | Next | Epic 2 | In Progress | Sprint 2 | Bootstrap | Added
3 | Removed | Maintenance | Planned investment required to address defects/updates/patching found in fielded IT Services | After next | Epic 3 | Done | Sprint 3 |  | Removed
5 |  | Technical Debt | Investment required to address issues in quality the IT Services we have in place today such as covering code with automated tests, re-factoring to improve code or make it testable |  | Epic 4 |  | Sprint 4
8 |  | Administration | Training, Team Meetings, Coaching/Mentoring, Company Events |  | Epic 5 |  | Sprint 5
13 |  | Incident | Restore existing IT Services to working order |  |  |  | Sprint 6
20 | [6 empty] | Sprint 7
40 | [6 empty] | Sprint 8
100 | [6 empty] | Sprint 9
? | [6 empty] | Sprint 10
Infinite

## Product Backlog
Rank | ID | Who / As A | What / I Want | Why / So That | Investment | Release Event | Scope | Value | Size | Project | Epic | Schedule | Committed | Status
1 | ST-001 | Operator | Do something exciting 1 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 13 | 3 | Centennial | Epic 1 | Sprint 1 | Committed | Done
2 | ST-002 | Operator | Do something exciting 2 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 13 | 2 | Centennial | Epic 1 | Sprint 1 | Committed | Done
3 | ST-003 | Operator | Do something exciting 3 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 8 | 5 | Centennial | Epic 1 | Sprint 1 | Committed | Done
4 | ST-004 | Operator | Do something exciting 4 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 5 | 8 | Centennial | Epic 1 | Sprint 1 | Committed | Done
5 | ST-005 | Operator | Do something exciting 5 | So I can finally go home on time | Project / New Feature | Bootstrap | Removed | 3 | 13 | Centennial | Epic 1 | Sprint 2 | Committed | Done
6 | ST-006 | Operator | Do something exciting 6 | So I can finally go home on time | Project / New Feature | Bootstrap | Added | 8 | 13 | Centennial | Epic 1 | Sprint 2 | Committed | Done
7 | ST-007 | Operator | Do something exciting 7 | So I can finally go home on time | Project / New Feature | Bootstrap | Added | 13 | 3 | Centennial | Epic 1 | Sprint 2 | Committed | Done
8 | ST-008 | Administrator | Stop someone from doing something 1 | So I can control people | Project / New Feature | Bootstrap | Baselined | 2 | 8 | Bootstrap | Epic 1 | Sprint 2 | Committed | Done
9 | ST-009 | Administrator | Stop someone from doing something 2 | So I can control people | Project / New Feature | Bootstrap | Baselined | 2 | 8 | Bootstrap | Epic 1 | Sprint 2 | Added | Done
10 | ST-010 |  | It’s a defect - fix it |  | Maintenance | Bootstrap | Added |  | 8 | Centennial | Epic 2 | Sprint 3 | Committed | Done
11 | ST-011 |  | It’s a defect - fix it |  | Maintenance | Bootstrap | Added |  | 5 | Centennial | Epic 2 | Sprint 3 | Committed | To Do
12 | ST-012 | Operator | Do something exciting 10 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 8 | 5 | Bootstrap | Epic 3 | Sprint 3 | Committed | Done
13 | ST-013 | Operator | Do something exciting 11 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 5 | 8 | Bootstrap | Epic 3 | Sprint 3 | Committed | Done
14 | ST-014 | Operator | Do something exciting 12 | So I can finally go home on time | Project / New Feature | Bootstrap | Removed | 3 | 13 | Bootstrap | Epic 3 | Sprint 3 | Committed | To Do
15 | ST-015 | Operator | Do something exciting 13 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 8 |  | Bootstrap | Epic 3 |  |  | To Do
16 | ST-016 | Operator | Do something exciting 14 | So I can finally go home on time | Project / New Feature | Bootstrap | Added | 13 |  | Bootstrap | Epic 3 |  |  | To Do
17 | ST-017 | Operator | Do something exciting 15 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 2 | 8 | Bootstrap | Epic 3 |  |  | To Do
18 | ST-018 | Operator | Do something exciting 16 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 2 | 8 | Bootstrap | Epic 3 |  |  | To Do
19 | ST-019 | Buyer | Support the corporate standard | So things end up costing more | Technical Debt | Bootstrap | Baselined | 13 | 5 | Bootstrap | Epic 3 |  |  | To Do
20 | ST-020 | Operator | Do something exciting 20 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 8 | 5 | Bootstrap | Epic 4 |  |  | To Do
21 | ST-021 | Operator | Do something exciting 21 | So I can finally go home on time | Project / New Feature | Bootstrap | Baselined | 5 | 8 | Bootstrap | Epic 4 |  |  | To Do
22 | ST-022 | Operator | Do something exciting 22 | So I can finally go home on time | Project / New Feature | Next |  | 3 | 13 | Bootstrap | Epic 4 |  |  | To Do
23 | ST-023 | Operator | Do something exciting 23 | So I can finally go home on time | Project / New Feature | Next |  | 8 | 20 | Bootstrap | Epic 4 |  |  | To Do
24 | ST-024 | Operator | Do something exciting 24 | So I can finally go home on time | Project / New Feature | Next |  | 13 | 8 | Bootstrap | Epic 4 |  |  | To Do
25 | ST-025 | Operator | Do something exciting 25 | So I can finally go home on time | Project / New Feature | Next |  | 2 | 8 | Bootstrap | Epic 4 |  |  | To Do
26 | ST-026 | Operator | Do something exciting 26 | So I can finally go home on time | Project / New Feature | Next |  | 2 | 8 | Bootstrap | Epic 4 |  |  | To Do
27
28

## Raw Calculations
Cycle / Release Event Current Data Calculations | Cycle / Release Event | Total Scope | Added Scope | Removed Scope | Total "Done" | Count with Estimates | Count without Estimates
Select Cycle / Release Event: | Bootstrap | 136 | 29 | 26 | 84 | 19 | 2
Sprint Current Data Calculations | Cycle / Release Event | Committed Velocity | Actual Velocity
Select Sprint: | Sprint 3 | 39 | 21

## Velocity History
Sprint Review Date | Sprint Number | Working Days (Number) | Team Size (Number) | Capacity (Hours) | Committed Velocity (Points) | Actual Velocity (Points) | Total Project Scope | Forecast Project Scope | Count with Estimates | Count without Estimates | Cumulative "Done" | Forecast "Done" | Unplanned (%) | Accuracy of Commit | Comments | 100% | Plus Range | Minus Range
2015-11-17 | 1 | 10 | 9 | 294 | 18 | 18 | 100 | #N/A | 13 | 2 | 18 | #N/A | 13% | 100% |  | 100% | 116% | 84%
2015-12-01 | 2 | 10 | 9 | 300 | 18 | 20 | 115 | #N/A | 16 | 0 | 38 | #N/A | 15% | 90% |  | 100% | 116% | 84%
2015-12-15 | 3 | 10 | 10 | 340 | 25 | 21 | 126 | #N/A | 19 | 2 | 59 | #N/A | 15% | 119% | Phil returned to team | 100% | 116% | 84%
2015-12-29 | 4 | [6 empty] | 139.6667 |  |  | #N/A | 79.3333 |  | #N/A |  | 100% | 116% | 84%
2016-01-12 | 5 | [6 empty] | 152.6667 |  |  | #N/A | 99.8333 |  | #N/A |  | 100% | 116% | 84%
2016-01-26 | 6 | [6 empty] | 165.6667 |  |  | #N/A | 120.3333 |  | #N/A |  | 100% | 116% | 84%
2016-02-09 | 7 | [6 empty] | 178.6667 |  |  | #N/A | 140.8333 |  | #N/A |  | 100% | 116% | 84%
2016-02-23 | 8 | [6 empty] | 191.6667 |  |  | #N/A | 161.3333 |  | #N/A |  | 100% | 116% | 84%
2016-03-08 | 9 | [6 empty] | 204.6667 |  |  | #N/A | 181.8333 |  | #N/A |  | 100% | 116% | 84%
2016-03-22 | 10 | [6 empty] | 217.6667 |  |  | #N/A | 202.3333 |  | #N/A |  | 100% | 116% | 84%
2016-04-05 | 11 | [6 empty] | 230.6667 |  |  | #N/A | 222.8333 |  | #N/A |  | 100% | 116% | 84%
2016-04-19 | 12 | [6 empty] | 243.6667 |  |  | #N/A | 243.3333 |  | #N/A |  | 100% | 116% | 84%
2016-05-03 | 13 | [6 empty] | 256.6667 |  |  | #N/A | 263.8333 |  | #N/A |  | 100% | 116% | 84%
2016-05-17 | 14 | [6 empty] | 269.6667 |  |  | #N/A | 284.3333 |  | #N/A |  | 100% | 116% | 84%
2016-05-31 | 15 | [6 empty] | 282.6667 |  |  | #N/A | 304.8333 |  | #N/A |  | 100% | 116% | 84%
2016-06-14 | 16 | [6 empty] | 295.6667 |  |  | #N/A | 325.3333 |  | #N/A |  | 100% | 116% | 84%
2016-06-28 | 17 | [6 empty] | 308.6667 |  |  | #N/A | 345.8333 |  | #N/A |  | 100% | 116% | 84%
2016-07-12 | 18 | [6 empty] | 321.6667 |  |  | #N/A | 366.3333 |  | #N/A |  | 100% | 116% | 84%
2016-07-26 | 19 | [6 empty] | 334.6667 |  |  | #N/A | 386.8333 |  | #N/A |  | 100% | 116% | 84%
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Formulas:
Sprint Review Date = [Sprint Review Date, row above]+14
Note on P1: hpsamios: Add comments to help you understand what happened during this Sprint so you can use the numbers better.

## Investment Allocation
Release Event | Bootstrap
Row Labels | Sum of Size
Maintenance | 13
Project / New Feature | 118
Technical Debt | 5
Grand Total | 136