## Slide 1: Comparison of Kanban And Scrum
Agile Stakeholder Participation Benefits
How are They the Same, Different and What Guidance Do You have On When tO Use What
Hans Samios @ Focussed Agile

## Slide 2: Scrum in a Nutshell
Split your organization
  small, cross-functional, self-organizing teams
Split your work
  small, concrete deliverables
  Assign someone to be responsible for that list and to sort the list by priority
  implementation team estimates the relative size of each item
Split time
  short fixed-length iterations (Usually 2 Weeks long, but Between 1 – 4 weeks)
  potentially shippable Solutions demonstrated after each iteration
Optimize the release plan
  update priorities in collaboration with the customer, based on insights gained by inspecting the release after each iteration
Optimize the process
  retrospective after each iteration.
Notes: Source: http://www.crisp.se/ScrumAndXpFromTheTrenches.html

## Slide 3: KanBan in a Nutshell
Visualize the workflow
  Split the work into pieces, write each item on a card and put on the wall
  Use named columns to illustrate where each item is in the workflow
Limit WIP (work in progress)
  Assign explicit limits to how many items may be in progress at each workflow state
Measure the lead time
  Lead Time (sometimes called “cycle time”) = average time to complete one item
  optimize the process to make lead time as small and predictable as possible
Notes: Source: http://availagility.wordpress.com/2008/10/28/kanban-flow-and-cadence/ - Karl Scotland

## Slide 4: Similarities Between Kanban and Scrum
Both are Lean and Agile
Both use pull scheduling
Both limit WIP
Both use transparency to drive process improvement
Both focus on delivering releasable Solutions early and often
Both are based on self-organizing (Stable) teams
Both require breaking the work into pieces
Both OPTIMIZE THE release plan continuously based on empirical data

## Slide 5: Differences Between Scrum And Kanban
Scrum | Kanban
Time-boxed iterations are prescribed | Time-boxed iterations optional. Can have separate cadences for planning, release, and process improvement. Can be event-driven instead of time-boxed.
Team commits to a specific amount of work for this iteration (Sprint) | Team commits to when it is brought into the board for execution
Uses Velocity as default metric for planning and process improvement | Uses Lead (or Cycle) time as default metric for planning and process improvement
Cross-functional teams prescribed | Cross-functional teams optional Specialist teams allowed
Items must be broken down so they can be completed within 1 Sprint | No prescribed item size
Burn-down chart prescribed | No particular type of diagram is prescribed
Change agent is “commitment” | Change agent is “WIP limits”
Notes: Source: https://www.crisp.se/file-uploads/Kanban-vs-Scrum.pdf – Henrik Kniberg

## Slide 6: Differences Between Scrum And Kanban (continued)
Scrum | Kanban
WIP limited indirectly Per Sprint | WIP limited directly Per workflow state
Estimation prescribed | Estimation optional
Cannot add items to ongoing iteration | Can add new items whenever capacity is available
A sprint backlog is owned by one specific team | A Kanban board may be shared by multiple teams or individuals
Prescribes 3 roles Product Owner, Scrum Master, Team | No prescribed roles
Prescribes 4 ceremonies Planning, Daily Scrum, Review and Retrospective | No prescribed ceremonies
A Scrum board is reset between each sprint | A kanban board is persistent
Prescribes a prioritized product backlog | Prioritization is optional
Notes: Source: https://www.crisp.se/file-uploads/Kanban-vs-Scrum.pdf – Henrik Kniberg

## Slide 7: Most Organizations and Teams Do a Combination of Both
Team Examples
  Kanban teams are set up as cross-functional
  Scrum teams Set WIP Limits within a Sprint
  Kanban Teams Setup cadence of retrospectives, Daily meetings, etc
  Scrum Teams establish (capacity-Based) rules for Break-fix or Other “interruptions”
Team-of-Teams (Scaling) Examples
  Kanban Teams commit to work on Sprint Schedule to aid in synchronization and Alignment
  Portfolio AND Program level work is set up as Kanban
Retrospectives drive improvement
  Scrum and Kanban as a Toolbox of Ideas to Leverage
  Use Whatever helps you improve

## Slide 8: Should We Use Scrum or Kanban?
Question | Kanban | Scrum
Primary Consideration: |  | 
Work for the team is more than 50% demand driven (team’s priority is responsiveness) | X | 
Work for the team is mostly project driven (team’s priority is predictability, forecasting and productivity) |  | X
Secondary Considerations: |  | 
Team questions value of estimation and planning | X | 
Team struggles to break items into small pieces |  | X
No / Low appetite for significant process change | X | 
Some / High appetite for significant process change |  | X
Teams usually set up majoring in either Scrum or Kanban and then evolve from there