## Notes
Purpose
Track some basic sprint statistics for multiple teams
What do the columns mean:
Team by team view showing
"Yesterday's Weather" is the approach that most agile teams use to determine how much they think they can get do in this sprint.
Idea: best predictor for the wather today is whatever happened yesterday
Discussion: At least you have the data point with yesterday (actual data) whereas anything else is a guess.
"Happy Stakeholder" is the viewpoint of some external person (manager, other stakeholder) who is looking at a sprint by sprint view of team making and meeting commitments
Idea: making and meeting commitments helps stakeholders
Idea: if we deliver more that expected, stakeholders will be happy
Discussion: would we have been better off using yesterdays weather as guess or the guess we have
"Velocity Variation" is the comparison between early sprints and later sprints in terms of velocity.
Idea: Are we getting better
Idea: This is a very bad public benchmark as it can be easily gamed
Discussion: Are we getting better and how do we know?
To add another team
Copy on of the tabs

## Velocity - Team 1
Team | Sprint | Planned | Actual | Variation from Team Plan / Commit | Acceptable Variation (Low) | Acceptable Variation (High) | Variance from "Yesterdays Weather" | "Happy Stakeholder" (ie did team meet commitment?) | Better Estimate ("Team" or "Yesterday's Weather"?) | Planned vs Actual Variation Within Acceptable Range | Velocity Variation (Compared to Median of First Sprints) | Median of First 3 Sprints
Team 1 | 1.1 | 36 | 31 | -13.89% | -16% | 16% | #N/A | Unhappy | #N/A | TRUE | 0% | 31
Team 1 | 1.2 | 42 | 37 | -11.9% | -16% | 16% | 19.35% | Unhappy | Team | TRUE | 19.35% | #N/A
Team 1 | 1.3 | 29 | 26 | -10.34% | -16% | 16% | -29.73% | Unhappy | Team | TRUE | -16.13% | #N/A
Team 1 | 1.4 | 32 | 27 | -15.62% | -16% | 16% | 3.846% | Unhappy | Yesterday's Weather | TRUE | -12.9% | #N/A
Team 1 | 1.5 | 32 | 24 | -25% | -16% | 16% | -11.11% | Unhappy | Yesterday's Weather | FALSE | -22.58% | #N/A
Team 1 | 2.1 | 21 | 21 | 0% | -16% | 16% | -12.5% | Happy | Team | TRUE | -32.26% | #N/A
Team 1 | 2.2 | 34 | 19 | -44.12% | -16% | 16% | -9.524% | Unhappy | Yesterday's Weather | FALSE | -38.71% | #N/A
Team 1 | 2.3 | 39 | 38 | -2.564% | -16% | 16% | 100% | Unhappy | Team | TRUE | 22.58% | #N/A
Team 1 | 2.4 | 38 | 32 | -15.79% | -16% | 16% | -15.79% | Unhappy | Team | TRUE | 3.226% | #N/A
Team 1 | 2.5 | 27 | 17 | -37.04% | -16% | 16% | -46.88% | Unhappy | Team | FALSE | -45.16% | #N/A
Team 1 | 3.1 | 32 | 18 | -43.75% | -16% | 16% | 5.882% | Unhappy | Yesterday's Weather | FALSE | -41.94% | #N/A

## Velocity - Team 2
Team | Sprint | Planned | Actual | Variation from Team Plan / Commit | Acceptable Variation (Low) | Acceptable Variation (High) | Variance from "Yesterdays Weather" | "Happy Stakeholder" (ie did team meet commitment?) | Better Estimate ("Team" or "Yesterday's Weather"?) | Planned vs Actual Variation Within Acceptable Range | Velocity Variation (Compared to Median of First Sprints) | Median of First 3 Sprints
Team 2 | 1.1 | 59 | 51 | -13.56% | -16% | 16% | #N/A | Unhappy | #N/A | TRUE | 0% | 51
Team 2 | 1.2 |  |  | #N/A | -16% | 16% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A