## PerStory
Issue Type | Story | Original Pt | Actual Pt | Over/Under | Sprint 2-2012 | 45 | 57
Story | Story 1 | 2 | 2 | 0 | Sprint 3-2012 | 31 | 40
Story | Story 2 | 3 | 3 | 0
Story | Story 3 | 5 | 3 | -2
Story | Story 4 | 5 | 3 | -2
Story | Story 5 | 1 | 1 | 0
Story | Story 6 | 3 | 3 | 0
Story | Story 7 | 1 | 1 | 0
Story | Story 8 | 1 | 2 | 1
Story | Story 9 | 1 | 1 | 0
Story | Story 10 | 5 | 5 | 0
Story | Story 11 | 3 | 8 | 5
Story | Story 12 | 5 | 2 | -3
Story | Story 13 | 2 | 8 | 6
Story | Story 14 | 3 | 2 | -1
Story | Story 15 | 3 | 2 | -1
Story | Story 16 | 1 | 3 | 2
Story | Story 17 | 3 | 5 | 2
Story | Story 18 | 2 | 2 | 0
Story | Story 19 | 3 | 3 | 0
Story | Story 20 | 1 | 1 | 0
Story | Story 21 | 13 | 8 | -5
Story | Story 22 | 3 | 3 | 0
Story | Story 23 | 5 | 2 | -3
Story | Story 24 | 1 | 2 | 1
Story | Story 25 | 3 | 2 | -1
Story | Story 26 | 2 | 2 | 0
Story | Story 27 | 2 | 3 | 1
Story | Story 28 | 2 | 3 | 1
Story | Story 29 | 5 | 3 | -2
Story | Story 30 | 5 | 8 | 3
Story | Story 31 | 3 | 2 | -1
Story | Story 32 | 3 | 2 | -1
Story | Story 33 | 1 | 1 | 0
Story | Story 34 | 5 | 5 | 0
Story | Story 35 | 2 | 2 | 0
Story | Story 36 | 2 | 2 | 0
Story | Story 37 | 1 | 1 | 0
Story | Story 38 | 1 | 3 | 2
Story | Story 39 | 2 | 1 | -1
Story | Story 40 | 2 | 1 | -1
Story | Story 41 | 3 | 3 | 0
Story | Story 42 | 3 | 5 | 2
Story | Story 43 | 8 | 5 | -3
Story | Story 44 | 2 | 5 | 3
Story | Story 45 | 1 | 0.5 | -0.5
Story | Story 46 | 3 | 2 | -1
Story | Story 47 | 8 | 2 | -6
Story | Story 48 | 5 | 3 | -2
Story | Story 49 | 8 | 2 | -6
Story | Story 50 | 3 | 1 | -2
Story | Story 51 | 0.5 | 0.5 | 0
Story | Story 52 | 3 | 3 | 0
Story | Story 53 | 1 | 2 | 1
Story | Story 54 | 3 | 3 | 0
Story | Story 55 | 3 | 3 | 0
Story | Story 56 | 3 | 3 | 0
Story | Story 57 | 13 | 13 | 0
Story | Story 58 | 5 | 5 | 0
Story | Story 59 | 5 | 5 | 0
Story | Story 60 | 3 | 8 | 5
Story | Story 61 | 1 | 5 | 4
Story | Story 62 | 3 | 8 | 5
Story | Story 63 | 2 | 2 | 0
Story | Story 64 | 8 | 5 | -3
Story | Story 65 | 13 | 5 | -8
Story | Story 66 | 2 | 3 | 1
Story | Story 67 | 1 | 0.5 | -0.5
Story | Story 68 | 3 | 3 | 0
Story | Story 69 | 3 | 2 | -1
Story | Story 70 | 3 | 2 | -1
Story | Story 71 | 13 | 13 | 0
Story | Story 72 | 5 | 5 | 0
Story | Story 73 | 2 | 5 | 3
Story | Story 74 | 1 | 3 | 2
Story | Story 75 | 5 | 13 | 8
Story | Story 76 | 3 | 8 | 5
Story | Story 77 | 5 | 2 | -3
Story | Story 78 | 5 | 5 | 0
Story | Story 79 | 8 | 3 | -5
Story | Story 80 | 3 | 3 | 0
Story | Story 81 | 3 | 5 | 2
Story | Story 82 | 3 | 5 | 2
Story | Story 83 | 2 | 3 | 1
Story | Story 84 | 3 | 5 | 2
Story | Story 85 | 3 | 2 | -1
Story | Story 86 | 2 | 5 | 3
Story | Story 87 | 2 | 5 | 3
Story | Story 88 | 1 | 2 | 1
Story | Story 89 | 8 | 13 | 5
Story | Story 90 | 2 | 1 | -1
Story | Story 91 | 2 | 5 | 3
Story | Story 92 | 3 | 1 | -2
Story | Story 93 | 1 | 2 | 1
Story | Story 94 | 3 | 2 | -1
Story | Story 95 | 3 | 2 | -1
Story | Story 96 | 3 | 2 | -1
Story | Story 97 | 3 | 2 | -1
Story | Story 98 | 5 | 3 | -2
Story | Story 99 | 3 | 2 | -1
Story | Story 100 | 3 | 3 | 0
Story | Story 101 | 5 | 5 | 0
Story | Story 102 | 1 | 0 | -1
Story | Story 103 | 5 | 5 | 0
Story | Story 104 | 2 | 2 | 0
Story | Story 105 | 8 | 5 | -3
Story | Story 106 | 5 | 8 | 3
Story | Story 107 | 8 | 8 | 0
Story | Story 108 | 8 | 8 | 0
Story | Story 109 | 5 | 5 | 0
Story | Story 110 | 1 | 1 | 0
Story | Story 111 | 3 | 3 | 0
Story | Story 112 | 3 | 3 | 0
Story | Story 113 | 1 | 1 | 0
Story | Story 114 | 8 | 8 | 0
Story | Story 115 | 8 | 3 | -5
Story | Story 116 | 5 | 5 | 0
Story | Story 117 | 1 | 1 | 0
Story | Story 118 | 5 | 3 | -2
Story | Story 119 | 2 | 2 | 0
Story | Story 120 | 3 | 3 | 0
Story | Story 121 | 2 | 1 | -1
Story | Story 122 | 3 | 3 | 0
Story | Story 123 | 3 | 3 | 0
Story | Story 124 | 1 | 1 | 0
Story | Story 125 | 5 | 5 | 0
Story | Story 126 | 5 | 5 | 0
Story | Story 127 | 8 | 13 | 5
Story | Story 128 | 13 | 8 | -5
Story | Story 129 | 5 | 8 | 3
Story | Story 130 | 5 | 5 | 0
Story | Story 131 | 3 | 5 | 2
Story | Story 132 | 13 | 13 | 0
Story | Story 133 | 13 | 3 | -10
Story | Story 134 | 1 | 1 | 0
Story | Story 135 | 1 | 1 | 0
Story | Story 136 | 1 | 1 | 0
Story | Story 137 | 2 | 2 | 0
Story | Story 138 | 5 | 5 | 0
Story | Story 139 | 8 | 13 | 5
Story | Story 140 | 3 | 13 | 10
Story | Story 141 | 3 | 1 | -2
Story | Story 142 | 13 | 8 | -5
| Story 143 | 13 | 20 | 7
| Story 144 | 8 | 20 | 12
| Story 145 | 8 | 20 | 12
| Story 146 | 13 | 8 | -5
| Story 147 | 3 | 3 | 0
| Story 148 | 3 | 3 | 0
| Story 149 | 2 | 3 | 1
| Story 150 | 3 | 3 | 0
| Story 151 | 1 | 3 | 2
| Story 152 | 3 | 5 | 2
| Story 153 | 3 | 3 | 0
| Story 154 | 3 | 2 | -1
| Story 155 | 8 | 20 | 12
| Story 156 | 8 | 13 | 5
| Story 157 | 5 | 5 | 0
| Story 158 | 3 | 5 | 2
| Story 159 | 5 | 8 | 3
| Story 160 | 1 | 1 | 0
| Story 161 | 8 | 8 | 0
| Story 162 | 3 | 13 | 10
| Story 163 | 5 | 5 | 0
| Story 164 | 2 | 3 | 1
| Story 165 | 5 | 8 | 3
| Story 166 | 5 | 8 | 3
| Story 167 | 5 | 8 | 3
| Story 168 | 1 | 3 | 2
| Story 169 | 3 | 5 | 2
| Story 170 | 8 | 13 | 5
| Story 171 | 3 | 8 | 5
| Story 172 | 2 | 2 | 0
| Story 173 | 5 | 5 | 0
| Story 174 | 5 | 5 | 0
| Story 175 | 5 | 5 | 0
| Story 176 | 3 | 3 | 0
| Story 177 | 5 | 3 | -2
| Story 178 | 1 | 2 | 1
| Story 179 | 2 | 5 | 3
| Story 180 | 8 | 3 | -5
| Story 181 | 2 | 3 | 1
| Story 182 | 8 | 8 | 0
| Story 183 | 5 | 13 | 8
| Story 184 | 8 | 8 | 0
| Story 185 | 3 | 3 | 0
| Story 186 | 5 | 5 | 0
| Story 187 | 5 | 3 | -2
| Story 188 | 3 | 5 | 2
| Story 189 | 8 | 8 | 0
| Story 190 | 2 | 2 | 0
| Story 191 | 3 | 13 | 10
| Story 192 | 3 | 3 | 0
| Story 193 | 8 | 8 | 0
| Story 194 | 5 | 5 | 0
| Story 195 | 3 | 5 | 2
| Story 196 | 5 | 5 | 0
| Story 197 | 802.5 | 909.5 | 107

## Frequency - Est vs Act
Row Labels | Count of Actual Pt
0.5 | 1
0.5 | 1
1 | 29
0 | 1
0.5 | 2
1 | 14
2 | 6
3 | 5
5 | 1
2 | 29
1 | 4
2 | 11
3 | 7
5 | 6
8 | 1
3 | 61
1 | 3
2 | 15
3 | 24
5 | 11
8 | 5
13 | 3
5 | 42
2 | 3
3 | 8
5 | 22
8 | 7
13 | 2
8 | 24
2 | 2
3 | 3
5 | 3
8 | 8
13 | 5
20 | 3
13 | 10
3 | 1
5 | 1
8 | 4
13 | 3
20 | 1
Grand Total | 196