## Instructions
Premise
Simple spreadsheet to display the Sprint Backlog and Sprint Burn-down.
Lookups Definition
In general you can use these out of the box for the basics.
Status: | Basic to-do to done progress across the board. Also includes "impediments" to signal blocks (use filter to find these)
Planned: | Is the work part of "planned" work for the Sprint, or the result of some kind of "external" interuption (unplanned). Note: does not count things that teams "discover" as they are doing work.
Team: | Members of the team that could take on tasks in the Sprint
Days In Sprint: | The number of days in the sprint, including planning, review and retrospective
Normal Variation: | When displaying the burn-down chart, is used to display what is considered a "normal variation". When the burn-down chart goes outside these lines, the team should consider action.
Working
Naming convention for Sprints - "Sprint_Review_Date(yyyy-mm-dd format) - Team_Name"
. E.g. 2015-11-17 - Penguins
. Allows for sorting of Sprints when you have multiple Sprints.
It is expected that you will need a new set of tabs for each Sprint, or perhaps just copy the spreadsheet and edit per sprint, and edit sprint name, team name in various places
Tabs are
. Tasks - a list of the tasks to be done in the Sprint. A view of the Sprint Backlog, one of the outputs of the Sprint Planning process.
. Burn-down - a chart showing the progress toward meeting the commitment per definition of done. Also includes range of "acceptable" values
. Unplanned - mechanism to track where our interuptions are coming from so we can adjust our practices. Reviews both the plan we established for "unplanned" work as well as completely "unplanned" items.
Enter the tasks in the "Tasks" tab first.
Then for items that are "unplanned", copy items to the "unplanned" sheet.
The hours are just a total hours spent on the unplanned task, not a remaining hours. Since these are usually small, the estimate is probably going to be pretty close to the actual.
Use filters at the top to search by "Impediments", "To Do", "Team", etc
When entering information, make sure the summations still work.
When colors are used (eg charts) typically "green is good; red is bad"
Potential Improvements
Could look at having automatic configuration of Sprint Length in tasks table based on the lookup.
Could look at having Sprint Name / Team Name as lookups on charts

## Lookups
Status | Planned? | Team | Days in Sprint | Normal Variation
To Do | Planned | Team Memeber 1 | 10 | 20%
In Progress | Unplanned | Team Memeber 2
Done |  | Team Memeber 3
Impediment |  | Team Memeber 4
Team Memeber 5
Team Memeber 6
Team Memeber 7
Team Memeber 8
Team Memeber 9 (SM)
Team Memeber 10 (PO)

## 2015-11-17 - Tasks
0 | Product Backlog Item | Task | Status | Assigned | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-09 | 2015-11-10 | 2015-11-11 | 2015-11-12 | 2015-11-13 | 2015-11-16 | 2015-11-17
1 | User story 1 | Task 1 | Done |  | 16
2 | User story 1 | Task 2 | Done |  | 16
3 | User story 1 | Task 3 | To Do |  | 2 | 2 | 2 | 2
4 | User story 1 | Task 4 | Done |  | 1 | 1 | 1
5 | User story 1 | Task 5 | In Progress |  | 16 | 16 | 16 | 16
6 | User story 1 | Task 6 | In Progress |  | 16 | 16 | 16 | 16
7 | User story 1 | Task 7 | To Do |  | 2 | 2 | 2 | 2
8 | User story 1 | Task 8 | Done |  | 1 | 1 | 1
9 | Small jobs | Task 1 | To Do |  | 1 | 1 | 1 | 1
10 | Small jobs | Task 1 | To Do |  | 1 | 1 | 1 | 1
11 | Small jobs | Task 1 | To Do |  | 1 | 1 | 1 | 1
12 | Small jobs | Task 1 | To Do |  | 2 | 2 | 2 | 2
13 | Small jobs | Task 1 | In Progress |  |  |  | 2 | 2
14 | Small jobs | Task 1 | Done |  |  | 1
15 | Small jobs | Task 1 | In Progress |  |  | 3 | 3 | 3
16 | User story 2 | Task 1 | Done |  | 1
17 | User story 2 | Task 2 | Done |  | 16
18 | User story 2 | Task 3 | Done |  | 2 | 2
19 | User story 2 | Task 4 | Done |  | 4 | 1
20 | User story 2 | Task 5 | Done |  | 2 | 2 | 2
21 | User story 2 | Task 6 | In Progress |  | 4 | 4 | 4 | 4
22 | User story 2 | Task 7 | To Do |  | 2 | 2 | 2 | 2
23 | User story 2 | Task 8 | To Do |  | 1 | 1 | 1 | 1
24 | User story 3 | Task 9 | To Do |  | 10 | 10 | 10 | 10
25 | User story 3 | Task 10 | To Do |  | 6 | 6 | 6 | 6
26 | User story 3 | Task 11 | In Progress |  | 8 | 8 | 8 | 8
27 | User story 3 | Task 12 | In Progress |  | 1 | 1 | 1 | 1
28 | User story 3 | Task 13 | In Progress |  | 2 | 2 | 2 | 2
29 | User story 3 | Task 14 | In Progress |  | 1 | 1 | 1 | 1
30 | User story 3 | Task 15 | In Progress |  | 1 | 1 | 1 | 1
31 | User story 3 | Task 16 | To Do |  | 6 | 6 | 6 | 6
32 | User story 3 | Task 17 | Done |  | 1
33 | User story 3 | Task 18 | Done |  | 1
34 | User story 3 | Task 19 | Done |  | 1
35 | User story 3 | Task 20 | To Do |  | 8 | 8 | 8 | 8
36 | User story 3 | Task 21 | In Progress |  | 16 | 16 | 16 | 16
37 | User story 3 | Task 22 | To Do |  | 8 | 8 | 8 | 8
38 | User story 3 | Task 23 | Done |  | 1
39 | User story 3 | Task 24 | Done |  | 1
40 | User story 3 | Task 25 | Done |  |  | 3
41 | User story 3 | Task 26 | Done |  |  | 1
42 | User story 3 | Task 27 | Done |  |  | 3
43 | User story 3 | Task 28 | In Progress |  |  |  | 3 | 3
44 | User story 3 | Task 29 | In Progress |  |  |  | 3 | 3
45 | User story 4 | Task 1 | To Do |  | 4 | 4 | 4 | 4
46 | User story 4 | Task 2 | Done
47 | User story 4 | Task 3 | Done
48 | User story 4 | Task 4 | In Progress |  |  |  |  | 1
49 | User story 4 | Task 5 | In Progress |  |  |  |  | 6
50 | User story 4 | Task 6 | In Progress |  |  |  |  | 2
51 | User story 4 | Task 7 | In Progress |  |  |  |  | 2
52 | User story 4 | Task 8 | In Progress |  |  |  |  | 2
53 | User story 4 | Task 9 | In Progress |  |  |  |  | 2
54 | User story 4 | Task 10 | To Do |  |  |  |  | 1
55 | User story 4 | Task 11 | Done |  | 16 | 16 | 16
56 | User story 4 | Task 12 | Done |  | 16 | 16 | 16
57 | User story 4 | Task 13 | Done |  | 8 | 8 | 8
58 | User story 4 | Task 13 | Done |  |  |  | 12
59 | User story 5 | Task 1 | Done |  | 1
60 | User story 5 | Task 2 | In Progress |  | 16 | 16 | 16 | 14
61 | User story 5 | Task 3 | In Progress |  | 16 | 16 | 16 | 16
62 | User story 5 | Task 4 | In Progress |  | 8 | 8 | 8 | 8
63 | User story 6 | Task 1 | In Progress |  | 8 | 4 | 1 | 1
64 | User story 6 | Task 2 | To Do |  | 1 | 1 | 1 | 1
65 | User story 6 | Task 3 | Done |  | 2 | 1
66 | User story 6 | Task 4 | To Do |  | 4 | 4 | 4 | 4
67 | User story 6 | Task 5 | In Progress |  | 2 | 2 | 2 | 2
68 | User story 6 | Task 6 | In Progress |  | 1 | 1 | 1 | 1
69 | User story 6 | Task 7 | To Do |  |  |  |  | 4
70 | User story 6 | Task 8 | To Do |  | 1 | 1 | 1 | 1
71 | User story 6 | Task 9 | To Do |  | 12 | 12 | 12 | 12
72 | Unplannned / Incoming | Task 1 | Done |  | 3
73 | Unplannned / Incoming | Task 1 | To Do |  | 4 | 4 | 4 | 4
74 | Unplannned / Incoming | Task 1 | Done |  | 2 | 2
75 | Unplannned / Incoming | Task 1 | In Progress |  | 4 | 4 | 4 | 4
76 | Unplannned / Incoming | Task 1 | To Do |  | 4 | 4 | 4 | 4
77 | Unplannned / Incoming | Task 1 | Done |  | 1
78 | Unplannned / Incoming | Task 1 | Done |  |  | 3 | 3
79 | Unplannned / Incoming | Task 1 | In Progress |  |  |  | 1 | 1
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
|  |  |  | Hours Remaining | 313 | 260 | 264 | 223 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | Pace | 313 | 278.2222 | 243.4444 | 208.6667 | 173.8889 | 139.1111 | 104.3333 | 69.5556 | 34.7778 | 0
|  |  |  | 20% above pace | 375.6 | 333.8667 | 292.1333 | 250.4 | 208.6667 | 166.9333 | 125.2 | 83.4667 | 41.7333 | 0
|  |  |  | 20% below pace | 250.4 | 222.5778 | 194.7556 | 166.9333 | 139.1111 | 111.2889 | 83.4667 | 55.6444 | 27.8222 | 0
Note on F1: HPS: Enter start day of Sprint. Assumes Wednesday to Tuesday 2 week Sprint

## 2015-11-17 - Unplanned
0 | Product Backlog Item | Task | Sprint Planning Status | Arrived | Hours
1 | Small jobs | Task 1 | Planned | 2015-11-04 | 1
2 | Small jobs | Task 1 | Planned | 2015-11-04 | 1 | Total hours (capacity): | 313
3 | Small jobs | Task 1 | Planned | 2015-11-04 | 1 | Planned Unplanned: | 11
4 | Small jobs | Task 1 | Planned | 2015-11-04 | 2 | Total Planned: | 302
5 | Small jobs | Task 1 | Planned | 2015-11-04 | 2 | Mid-sprint Added Unplanned: | 22
6 | Small jobs | Task 1 | Planned | 2015-11-04 | 1
7 | Small jobs | Task 1 | Planned | 2015-11-04 | 3
8 | Unplannned / Incoming | Task 1 | Unplanned | 2015-11-05 | 3
9 | Unplannned / Incoming | Task 1 | Unplanned | 2015-11-05 | 4
10 | Unplannned / Incoming | Task 1 | Unplanned | 2015-11-05 | 2
11 | Unplannned / Incoming | Task 1 | Unplanned | 2015-11-05 | 4
12 | Unplannned / Incoming | Task 1 | Unplanned | 2015-11-05 | 4
13 | Unplannned / Incoming | Task 1 | Unplanned | 2015-11-06 | 1
14 | Unplannned / Incoming | Task 1 | Unplanned | 2015-11-06 | 3
15 | Unplannned / Incoming | Task 1 | Unplanned | 2015-11-06 | 1
16
17
18
19
20
21
22
23
24
25
26
28
29
30
31
32
33
35
36
37
38
39
41
42
43
44
45
46
47
48
49
50
51
33
33
39.6
26.4
22
22
11